## Slide 1: Globe Maximo - Streamline Integration
Project Calendar
Notes: Sep 15, 2020 – Oct 15, 2020

## Slide 2: January 2021
Completed
Not Started
Ongoing
Schedule elapsed / Off Track
Current Day
SUN | MON | TUE | WED | THU | FRI | SAT
 |  |  |  |  | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30
UAT with Proponent
Mock-up UAT with PM
Mock-up UAT with PM
Alignment of Upcoming Activities and Project Timeline
UAT with Proponent
Mock-up UAT with PM
UAT With Proponent Sign Off

## Slide 3: February 2021
Completed
Not Started
Ongoing
Schedule elapsed / Off Track
Current Day
SUN | MON | TUE | WED | THU | FRI | SAT
 | 1 | 2 | 3 | 4 | 5 | 6
7 | 8 | 9 | 10 | 11 | 12 | 13
14 | 15 | 16 | 17 | 18 | 19 | 20
21 | 22 | 23 | 24 | 25 | 26 | 27
28 |  |  |  |  |  | 
Cutover Planning Activities
Go Live
Production Migration
Production Migration
CAB Review and Approval
Post-Go Live Support
Post-Go Live Support
Post-Go Live Support

## Slide 4: March 2021
Completed
Not Started
Ongoing
Schedule elapsed / Off Track
Current Day
SUN | MON | TUE | WED | THU | FRI | SAT
 | 1 | 2 | 3 | 4 | 5 | 6
7 | 8 | 9 | 10 | 11 | 12 | 13
14 | 15 | 16 | 17 | 18 | 19 | 20
21 | 22 | 23 | 24 | 25 | 26 | 27
28 |  |  |  |  |  | 
Post-Go Live Support
Post-Go Live Support
Project Closure Sign Off
Project Closure Sign Off

## Slide 5: Cutover Activities
Activities | Responsible | Description
Method of Procedure (MoP) Creation | MDI | Migration steps documentation
Review Security Profiles of Users | MDI/NTG Spare Mgt/Maximo Platform Owner | Determine Application Access
Data Alignment of Operating Locations between Maximo and Streamline | NascTech/NTG Spares Mgt/Maximo Platform Owner | Locations Master Data to be sync
Data Alignment of Item and Item Balances between Maximo and SAP | NascTech/NTG Spares Mgt/Maximo Platform Owner | Item Master and Item Balances Data to be sync
Data Alignment of Storeroom, Item, Inventory Balances between Maximo and Streamline | NascTech/NTG Spares Mgt/Maximo Platform Owner | Master data to be sync
Actual Data Entry for Spares Request, Issuance, and Return Requests Transactional Data | NascTech/NTG Spares Mgt/Maximo Platform Owner | No test data will be recorded. Globe Business As Usual (BAU) Group should perform the actual steps in Maximo